## Slide 1
GROUP CODE · SURGE 090
First Progress Review (Design & Development Phase)
Smart Snake Robot
with Dynamixel Smart Servo Motors
Shashank Jangir
ENTRY NO.
2024EE11048
Bhavesh Bansiwal
ENTRY NO.
2024ME10487
Mahima Chotiya
ENTRY NO.
2024ME11187
INSTITUTION
Indian Institute of Technology, Delhi
PROJECT GUIDE
Professor Amartansh Dubey
PROJECT REPOSITORY
https://github.com/shashankjangir/surge090
Notes: Title slide for the 25% progress review of the Smart Snake Robot project, Group SURGE 090. Introduce the team and milestone scope.

## Slide 2
ACTUATOR SELECTION STUDY
Why Dynamixel Motors?
THE REQUIREMENT
A snake robot drives many joints at once. The actuator must deliver:
Precise position control
Simple wiring architecture
Scalability for multiple joints
Reliable communication
Real-time feedback
Compact size & sufficient torque
OPTIONS COMPARED
Criterion | Conventional Servo | Dynamixel Smart Servo
Communication | Individual signal wire per motor | Daisy-chain communication
Wiring Complexity | High | Low
Feedback | Not available | Position, load, temperature, voltage feedback
Controller | External controller required | Built-in controller
Scalability | Difficult for many joints | Designed for multi-joint robots
Precision | Moderate | High
Robotics Applications | Hobby projects | Research and industrial robotics

## Slide 3
ARCHITECTURE & DECISION
Daisy-Chain Architecture & Final Selection
Conventional Servo — Separate Wiring
Controller
Servo 1
Servo 2
Servo 3
Servo 4
Every motor needs its own signal wire back to the controller.
Dynamixel — Daisy-Chain
Ctrl
M1
M2
M3
M4
One cable carries power and data to every joint in sequence.
KEY LEARNINGS
Daisy-chain wiring sharply cuts cabling and assembly effort.
A controller built into every motor simplifies integration.
Real-time feedback enables future closed-loop control.
Compact form factor suits modular robot segments.
High precision and smart control fit advanced robotics.
FINAL SELECTED ACTUATOR
Dynamixel XL330 Series
Chosen for its smart serial communication, full-state feedback, compact form factor and effortless multi-joint scaling — the right fit for a multi-segment snake robot.

## Slide 4
GOALS & EXPECTED OUTCOMES
What This Project Sets Out to Build
01
Modular Architecture
A repeatable segment-based mechanical design.
02
Dynamixel Actuators
Integrate smart servos with daisy-chained control.
03
Raspberry Pi Control
A single-board-computer control system.
04
Locomotion Algorithms
Implement serpentine and gait-based motion.
05
Sensor Integration
Add sensing for future intelligent navigation.
06
Scalable Platform
Keep it maintainable and easy to extend.
Notes: Six concrete goals across mechanics, actuation, computing, control, sensing and scalability. These map to the timeline phases.

## Slide 5
WORK COMPLETED SO FAR
Quarter-One Progress Summary
OVERALL COMPLETION
25 %
Phase 1 complete · Phase 2 underway
10
Tasks done
2
Segments printed
1
Pi configured
COMPLETED TASKS
Literature review & project understanding
Hardware selection & BOM preparation
CAD design of snake-robot segment
Assembly sized to Dynamixel XL330 dims
3D printing of two prototype segments
Raspberry Pi setup & configuration
Wi-Fi connectivity testing on the Pi
Basic Raspberry Pi lab projects executed
GitHub repository created & maintained
Procurement process initiated
Notes: About a quarter done: ten tasks closed across research, mechanical design, fabrication and the compute platform.

## Slide 6
Power Supply
Raspberry Pi 5 [Central Controller]
Communication Layer (U2D2 / UART)
Dynamixel Motor Network
Robot Segments (10 × servo joints)
Control Algorithms
IMU / Force Sensors
Camera Module
Wireless Control Module
LEGEND
Implemented
In Progress
Planned Future Work
Current Implementation Status
Raspberry Pi 5 configured and tested
Communication architecture defined
Mechanical segments fabricated
Dynamixel integration pending hardware
SYSTEM ARCHITECTURE
Conceptual Block Diagram
Architecture finalized · Implementation in progress
FUTURE INTEGRATION
Notes: Controller at the centre. Solid cyan = implemented/in progress; dashed amber (sensors, camera) = designed-in but scheduled for a later phase.

## Slide 7
CAD DESIGN DEVELOPMENT
A Segment Designed Around the Motor
The CAD model is built to the exact dimensions of the Dynamixel XL330-M288 servo, using a modular, segment-based architecture focused on manufacturability and scalability.
DESIGN CONSIDERATIONS
Motor mounting — Precise seats for XL330 servo bodies.
Structural rigidity — Stiff frame to resist motion loads.
Cable routing — Clean daisy-chain channels for wiring.
Electronics ready — Space reserved for future boards.
ASSEMBLY FLOW
Motor → Segment Parts → Full Chain Assembly
① Motor
② Segment Parts
③ Full Assembly
③ Full Assembly
Notes: CAD modelled to real XL330 dimensions so printed parts mate with the actual servos. Replace the placeholder with CAD screenshots.

## Slide 8
PROTOTYPE FABRICATION
From Model to Printed Hardware
PRINTED SEGMENT — PHOTO 1
Insert photo of the first 3D-printed segment
PRINTED SEGMENT — PHOTO 2
Insert photo of the second segment / assembly
FABRICATION STATUS
Two prototype segments 3D printed
Both segments produced from the CAD model.
DONE
Initial dimensional verification done
Printed parts measured against design specs.
DONE
Physical validation of CAD initiated
Checking fit, tolerances and assembly.
NEXT
Preparing for motor-integration tests
Next: seat XL330 servos into segments.
NEXT
Notes: Two segments printed and measured, validating the CAD. Next step is servo integration. Drop prototype photos on the left.

## Slide 9
Raspberry Pi 5 received & configured
Raspberry Pi OS installation completed
Wi-Fi connectivity established
SSH & remote access explored
Basic GPIO & intro projects performed
Linux environment & Python familiarity
Raspberry Pi Platform Successfully Configured and Tested
Raspberry Pi OS Desktop
GPIO / Python Testing
SSH Remote Access
System Configuration
Development Environment Setup
PROGRESS MILESTONES
Standing Up the Compute Platform
RASPBERRY PI LEARNING & DEVELOPMENT
Notes: Control computer is live: OS installed, networked, remotely accessible, exercised with intro GPIO and Python. De-risks software before motors arrive.

## Slide 10
HARDWARE PROCUREMENT & RESOURCE AVAILABILITY
Hardware Procurement & Resource Availability
Hardware Strategy: Raspberry Pi 4 was planned in the BOM; however, a Raspberry Pi 5 was already available in the laboratory, enabling immediate software development and testing without waiting for delivery. To accelerate development, the team utilised the laboratory Raspberry Pi 5 platform while the ordered components remain under procurement.
AVAILABLE & IN USE
ORDERED — AWAITING DELIVERY
COMPLETED PREPARATORY WORK
Raspberry Pi 5 (Laboratory Resource)
Raspberry Pi Starter Kit
Raspberry Pi OS Environment
GitHub Repository
3D Printed Prototype Segments
Dynamixel XL330 Smart Servo Motors
U2D2 Communication Interface
U2D2 Power Hub Board
Dynamixel Communication Cables
5V Power Supply
ESP32 Development Board
Hardware selection finalised
Bill of Materials prepared
CAD model completed
Segment fabrication initiated
Software environment configured
DEVELOPMENT PROGRESS
✓
Component
Selection
✓
Procurement
Initiated
✓
CAD
Design
✓
Prototype
Printing
✓
RPi
Learning
⏳
Motor
Integration
Awaiting HW
→
Locomotion
Testing
Upcoming
★
Key Achievement: Although the primary Dynamixel hardware has not yet arrived, the team has successfully utilised available laboratory resources to complete design, fabrication, documentation, and software preparation activities, ensuring project progress is maintained.
Notes: Live BOM from the purchasing sheet. Compute hardware in hand; actuation and power chain ordered. Total approx Rs 33,760.

## Slide 11
REPOSITORY & DOCUMENTATION
Version Control From Day One
1
Repository created
Central home for the whole project.
2
Version control established
Tracked, reversible change history.
3
CAD files uploaded
Design source committed to the repo.
4
Design iterations documented
Every revision captured in commits.
5
Progress tracking in place
Milestones and issues logged.
6
Team collaboration workflow
Shared branches and pull requests.
GitHub repository — project root & structure
Commit history — tracked iterations & uploads
GITHUB REPOSITORY SCREENSHOTS
✓ All milestones tracked in GitHub
Notes: The repo is the single source of truth — CAD, docs, tracked iterations — with a collaboration workflow already running.

## Slide 12
PROJECT TIMELINE
Eight Phases · Currently at 25%
PHASE 1
Research & Design
Completed
1
PHASE 2
Hardware Procurement
In progress
2
PHASE 3
Mechanical Assembly
Up next
3
PHASE 4
Motor Integration
4
PHASE 5
Control Algorithms
5
PHASE 6
Sensor Integration
6
PHASE 7
Testing & Optimisation
7
PHASE 8
Final Demonstration
8
WE ARE HERE
Notes: Eight-phase plan: Phase 1 complete, Phase 2 active, Phase 3 next — about 25%. Phases 4-8 cover integration, control, sensing, testing, demo.

## Slide 13
CURRENT ACHIEVEMENTS
Concrete Wins in Quarter One
Architecture finalized
System block diagram locked.
CAD design completed
Segment modelled to motor specs.
Prototype fabrication started
Two segments printed & checked.
Pi environment established
OS, network and tooling ready.
GitHub workflow operational
Version control and docs live.
Procurement initiated
Core compute received; rest ordered.
Notes: Six headline achievements: design, fabrication, compute, tooling and procurement all moving — a working foundation.